Evaluation Framework for the Delivery Phase

We have accounted for an Evaluation Consultant to come in and deliver a strong process during the Delivery Phase, however, the below framework sets out some initial goals and potential KPIs for evaluating those goals. The initial task for the Evaluation Consultant will be to consider what we have outlined in this plan and from there work with the Project Manager in order to create a logic model which will form the basis of a strong evaluation.

1. Key Performance Indicators (KPIs):

- Visitor numbers and demographics.

- Engagement levels through all activities.

- Revenue generation from admissions, merchandise, and sponsorship.

- Community participation, particularly from underrepresented groups.

- Digital engagement metrics for online resources.

2. Visitor Feedback:

- On-site surveys and digital feedback forms to assess visitor satisfaction, learning outcomes, and accessibility.

3. Stakeholder Consultations:

- Regular meetings with partner organisations, funders, and community groups to monitor progress and address concerns.

- Evaluation reports submitted to funding bodies.

4. Financial Performance:

- Quarterly budget reviews comparing projected and actual spending.

- Analysis of revenue streams to ensure financial sustainability.

5. Educational and Outreach Metrics:

- Participation rates in workshops and educational programmes.

- Feedback from schools, clubs, and community groups on the quality and relevance of content.

6. Long-Term Impact:

- Tracking the economic benefits to the region through tourism and local partnerships.

- Assessing the project’s contribution to community pride and heritage preservation.

In addition to the above measurable tasks, the Association intends to enhance knowledge sharing by publishing evaluation findings in reports and case studies and hosting debriefing sessions with stakeholders to share lessons learned.

Similarly, we are keen to continuously improve by providing iterative updates to project activities based on evaluation findings and develop legacy plans to maintain and build on the project’s successes post-delivery.

Implementation:

- Assign clear responsibilities for data collection and analysis within the project team.

- Use tools such as visitor counters, online analytics platforms, and financial software to streamline monitoring.

- Schedule periodic evaluation checkpoints to ensure alignment with objectives.

Activity Action Plan

See next page

| Activity - detailed description | Audiences | Outcomes | Resources | Total Cost | Timetable | Targets & Measures of success | Methods of Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Theme: Origins |  |  |  |  |  |  |  |
| Shinty’s Stories - Community Stories Grant Scheme - Sgeulachdan na camanachd - Sgeama Ghrantaichean son sgeulachdan coimhearsnachd Grant fund to offer 10x£1k grants to Shinty Clubs/Shinty Memories Organisations for local workshops to gather community stories, images, video footage etc. to create living shinty archive & refreshed community cases in exhibition. | Potential volunteers Shinty Memories groups Local Shinty Clubs Former shinty players | Heritage is valued and better understood Heritage is protected, conserved and revitalised All communities are supported to explore and share their heritage Exhibition refresh encourages more repeat visitors People will have learned skills | Project Manager time Heritage co-ordinator time - £2000 (8 days @ £250) £10k Grant fund costs Lateral North time (exhibition template handbook) | £12000 | July 2025 - June 2027 | 6 community exhibition cases created Aspire to engage at least 4 participants min. from each successful participating group (40 total min.) Archive established using core standard procedures | Feedback questionnaire. Record participant details to track retention and re-engagement across other project activities. Exhibition visitor feedback forms |
| Caman Connections -Ceanglan Camanachd Oral history collecting using Community Gatherings/Shinty Memories activities to identify potential participants (interviewers & interviewees). Train volunteers to undertake oral history & work with Digital Officer to collect memories and stories from shinty community incl women’s stories, Gaelic, winter heritage of shinty. Work with MHH ICH working group to forge connections for working to best practices in working with ICH | Potential volunteers Gaelic learners Fluent Gaelic speakers Shinty Memories groups Scottish diaspora | Heritage is valued and better understood Heritage is protected, conserved and revitalised All communities are supported to explore and share their heritage Heritage information is more accessible Shinty Memories groups strengthened Volunteers recruited | Professional fees for oral history training sessions – 1 day @ 4 locations at £300 per day incl travel and use of equipment: £1200 Heritage co-ordinator 8 days @ £250 £2000 Digital Officer time – 10 days | £3200 | October 2025 – June 2025 | Minimum 8 oral history interviews collected, summarised and documented Min 4 volunteers committed to ongoing volunteering 6 podcast episodes created and broadcast Shinty archive established and developed in Highland Archive Service | Listening/engagement figures for podcast series Comments and analytics from online platforms 1-2-1 interviews with participants on quality and impact of training & participation Feedback questionnaire. Record participant details to track retention and re-engagement across other project activities |
| Inverness Shinty Trail - Shinty trail Slighe -Camanachd Inbhirnis digital walking trail of shinty landmarks and activity around Inverness linking Bught Park with Inverness Castle providing a physical connection between these two new visitor experiences in Inverness. | Tourists & visitors to the area Families (Inverness & environs) Bught Park users | Heritage is valued and better understood All communities are supported to explore and share their heritage Heritage information is more accessible Partnerships with Heritage and Cultural Organisations | Project Manager time Costs of trail production (held with Inverness Castle project) | £0 | July-September 2025 | 250 people adding the trail to their ‘collection’ on Spirit of the Highlands website. | No.s accessing digital trail Feedback forms at exhibition gathering visitor statistics |
| ‘Stick to Shinty’ talk series - Caman gu Caman - sreath de thachartasan is òraidean An informal talks programme will be developed to include a diverse set of speakers and subjects & made available virtually for a remote audience (may include: Talks in Gaelic language; Talks that include women’s stories around shinty culture; Talks on community heritage of shinty i.e. the winter sport; Talks on the heritage crafts associated with shinty Train club volunteers to deliver talks so that they can share the unique heritage of their own club. | Shinty fans General sports fans (not previously engaged with shinty) Gaelic speakers learners & fluent Scottish diaspora Tourists & visitors to the area General public | Heritage is valued and better understood All communities are supported to explore and share their heritage Heritage information is more accessible Gaelic language promoted | Project Manager time Speaker fees @ £200 each | £1600 | Oct 2025 – June 2007 | 8 talks delivered over project period Min 4 volunteers committed to ongoing volunteering | Printed & digital feedback forms. Observation & counting participant numbers Volunteer feedback forms |

| Activity - detailed description | Audiences | Outcomes | Resources | Total Cost | Timetable | Targets & Measures of success | Methods of Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Theme: Community |  |  |  |  |  |  |  |
| Annual Shinty Memories Gathering - Reception event planned, organised and led by the Camanachd Association to bring Shinty Memories groups together. Year 1 at Bught Park, Year 2 roadshow event. Quiz, object handling viewing of an old match, ‘pie & pint’. Volunteers are recruited to support planning of these events. | Shinty Memories groups Former players Potential volunteers | Heritage is valued and better understood People have come together and connected with local heritage All communities are supported to explore and share their heritage CA is better connected with ‘on the ground’ heritage People feel more valued and included | Project Manager time Volunteer time Travel grant - £500 Hospitality costs – £750 | £1250 | Week before season starts, Feb End. | 2 gatherings held - winter/off season between 2025 & 2027 Aspiration of min 4 volunteers committed to ongoing volunteering | Printed & digital feedback forms. Volunteers will distribute and collect written responses to a standard question set to gauge enjoyment and engagement at each event. Observation & counting participant numbers Informal feedback from CA staff, volunteers and members who will be encouraged to document any informal verbal feedback. |
| Shinty Awards - Hall of Fame - Duaisean na Camanachd Legacy award that honours past players. Inspired by Mowi Awards & connects to heritage - vintage players, heritage volunteers. Publicly nominated with the addition of an ‘all stars’ or ‘hall of fame’ nomination. A heritage award will also be added | Shinty Memories groups Former players Local shinty clubs Shinty fans Potential volunteers | Heritage is protected, conserved and revitalised People have come together and connected with local heritage People are empowered to preserve their cultural legacy. Volunteers recruited | Project Manager time Digital Officer time | £0 | Start of November | Legacy award established as annual event Social media campaign on shinty legends Hall of Fame nominations | No.s people engaging with campaign and nominating Feedback from local shinty clubs on engagement levels |
| Digital/web - Ùrachadh didsiteach agus làrach-lìn Restructure of website to give higher priority to community & heritage. Retitling of ‘History’ page to ‘Community & Heritage’ Increase links on the page to existing external resources and partners. Signpost to specific shinty memories groups and how to contact them. Signpost to new exhibition. Promote Gaelic more highly on website. Explain heritage & meaning of the various cups listed. Lead on social media promotion, sign posting and sharing of smaller clubs’ and shinty memories’ community events. | General public Scottish diaspora Tourists & visitors to area Gaelic speakers General sports fans | Heritage is valued and better understood All communities are supported to explore and share their heritage Heritage information is more accessible Partners more visibly connected i.e. Leap Sports, Pride of the Terraces, charters etc. CA has an improved network of partners | Project Manager time Digital Officer time Web developer time - £1000 | £1000 | Complete by Spring 2026 | Newly restructured website with higher profile of Heritage & Community 10% increase in engagement with website | Web analytics - no. of visitors, no. of pages, length of visit |

| Activity - detailed description | Audiences | Outcomes | Resources | Total Cost | Timetable | Targets & Measures of success | Methods of Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Theme: Competition |  |  |  |  |  |  |  |
| Playing the Game - Cluich na Camanachd Supporting the work of the Camanachd Association through the competitive sport. Recognising that the playing of the game is itself protecting the heritage of the game. Gaelic is promoted as a key conduit to provide skills training. Train new volunteers to support the development of the game, including coaches and officials. | Shinty fans & spectators People from identified centres of urban deprivation (Inverness) Young people Potential volunteers Gaelic learn | People have come together and connected with local heritage All communities are supported to explore and share their heritage Heritage is protected, conserved and revitalised | Project Manager time Shinty Development Officers time | £0 | July 2025 – June 2027 | 1000 people attending cup finals at Bught Park. Increase of 5% in total membership on an annual basis. Aspiration of min 4 volunteers committed to ongoing volunteering | Number of registered members. Increased cup final attendance on 5 year average. Number of teams/schools participating. Number of registered coaches. Number of registered officials. |
| Cup Final - Cuairt Dheireannach Cupa na Camanachd To capitalise on 2025 Cup Final and new exhibition. Partnership with Highlife Highland’s Am Baile bilingual digital archive to run a social media campaign highlighting images/stories from their archives and supported by images/ excerpts/audio from new exhibition with the aim of generating interest and curiosity about the new exhibition. Key opportunities for volunteering. | Families -Inverness & environs. Under represented people General sports fans Shinty fans & spectators Potential volunteers | Heritage is valued and better understood People have come together and connected with local heritage | Project Manager time Digital Officer time HLH archivist (Am Baile) time | £0 | July – Oct 2025 | Social media campaign created People respond positively to exhibition Exhibition Video teasers created by Digital Officer 500 visitors to exhibition on Cup Final Day 4 dedicated volunteers recruited for exhibition opening day | Stats on engagement with campaign online Monitor social media analytics Feedback questionnaire at exhibition |
| All Star Veteran’s Friendly - Càirdeas na Laoch Annual Summer veteran players’ friendly matches to be played home/away i.e. North/South. Short walking shinty sixes match and shinty skills challenges for older or less mobile veterans, and a reception. Train volunteers in stewarding and event management with the view to creating a team to support this new venture. Restoration of old cups for new competitions. | Former shinty players Shinty Memories groups Families (inverness & environs) Potential volunteers | Heritage is valued and better understood Heritage is protected, conserved and revitalised All communities are supported to explore and share their heritage People have come together and connected with local heritage | Project Manager time Shinty Development Officers time Shinty Heritage Committee time Digital officer time Travel support costs £500 | Pitch hire: £500 Insurance costs for players: £350 | July 2025 – June 2027 | 2 Events – 2026 & 2027 No.s attending events Aspiration of min. 5 volunteers supporting planning & running events | Feedback questionnaires Video interviews with participants |

| Activity - detailed description | Audiences | Outcomes | Resources | Total Cost | Timetable | Targets & Measures of success | Methods of Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Theme: Futures |  |  |  |  |  |  |  |
| Digital Learning Pack - Pasgan ionnsachaidh didsiteach Creation of bilingual digital learning resource, aimed primarily at schools and also for informal learning settings to dynamically connect with young people from across Scotland, particularly those in more rural, disparate communities that may never have the opportunity to visit the exhibition in person.. Through the banner ‘play, learn, explore and discover the sport of shinty’, making exhibition core themes to young audiences learning about shinty for the first time or building learning shinty’s core community values. | Young people – formal & informal learning Gaelic -learners & fluent Shinty Memories groups Scottish diaspora Shinty youth teams Under represented groups | Heritage is valued and better understood People have come together and connected with local heritage All communities are supported to explore and share their heritage Young people can actively engage with heritage | Project Manager time Heritage education/learning specialist time 12 days @ £300 £3600 Digital web developer time 12 days @ £300 £3600 Marketing and publicity | £7700 | Launched for academic school year 2026 | 8 schools per year taking up learning resource. Positive feedback from teachers. Increased interest in the sport/willingness to engage. | Classroom engagement no.s Online engagement no.s Bespoke feedback forms for young people, teacher & educator feedback following workshops and through resource use. Teacher feedback - targeted questionnaires distributed to selected schools |
| New Faces - Come & Try - Aghaidhean ùra Sessions to offer opportunities for more people to play and enjoy shinty in a supported but non-competitive environment. This activity will support engaging with underrepresented groups to identify people looking for social and sporting activity. | Under represented groups People from identified areas of urban deprivation | All communities are supported to explore and share their heritage People have come together and connected with local heritage Shows CA commitment to being interested in these groups & playing for fun and community Capacity, skills and expertise in heritage has been built through collaborating with partners CA has an improved network of partners and professionals in the heritage and voluntary sectors | Project Manager time (to engage with community groups, organise inclusion training etc.) SDO time to deliver sessions & coaching Third Sector organization resources/time i.e.3rd Sector Interface |  | July 2025 – June 2027 | One event for each identified community (1. & 2.) yearly - total 4 events. 5% of participants in sessions go on to join a shinty club. | Feedback questionnaire. Record participant details to track retention and re-engagement across other project activities. Evaluation from partner agencies supporting initiatives – learning collated into final report. |
| Shinty Challenges - Dùbhlain na Camanachd Volunteer drive to encourage people to get involved. Pop-up stand at Camanachd Cup Final, international matches, Highland Games and other relevant events Shinty Development officers and local young players demonstrate skills with invitation to ‘come and try’ with competitive skills challenges (such as the longest shy, most keepy uppies etc.) | General sports fans Young people Tourists and visitors to the area Local shinty club volunteers Potential volunteers | Heritage is valued and better understood Heritage is protected, conserved and revitalised People have come together and connected with local heritage Heritage information is more accessible | Project Manager time Shinty Development Officers time Digital Officer time – promoting events Promotional materials – pop-up/stand - Lateral North design & produce | £750 | July 2025 – June 2027 | Year 1 - 4 events Year 2 - 6 events (to include either Belladrum and/or HebCelt) Min 50 people engaging at each event with ‘challenge’ activities Over 65% of people reacting positively to the Challenges. Aspiration of 4 volunteers to support each event | Rapid feedback forms. Observational feedback. Record engagement numbers. |

| Exhibition - detailed description | Audiences | Outcomes | Resources | Total Cost | Timetable | Targets & Measures of success | Methods of Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Overall Exhibition Impact & Evaluation |  |  |  |  |  |  |  |
| Increased Awareness and Understanding of Shinty’s Heritage – The exhibition will provide a structured, engaging journey through shinty’s history, traditions, and significance, ensuring a deeper appreciation of the sport’s cultural value. | Sports fans Gaelic learners & speakers Families Diaspora Tourists & visitors Shinty fans Former players Volunteers | Heritage is valued and better understood Visitors leave with an enhanced knowledge of shinty’s role in the fabric of Scottish culture. | Exhibition Delivery Officer Range of exhibition fit out resources which are fully detailed in the Project Budget. | Covered in exhibition fit-out budget | July 2025 - Ongoing | Visitor surveys indicate at least 75% feel they have learned something new, have enjoyed the experience and have a greater understanding of the significance of shinty. 5,000 online interactions with the exhibition materials in the first year. | Online and social media analytics Observational studies Exhibition visitor feedback forms |
| Encouraging Participation in Shinty – The exhibition’s interactive elements, particularly Tier 3, will serve as an entry point for new participants to take up shinty, encouraging lifelong engagement with the sport. | Young people Schools Sports fans General visitors | Increased participation in grassroots shinty Volunteers and new players recruited Strengthening of local shinty clubs | Local club shinty coaches Shinty equipment Training equipment (cones, goals etc.) | £20 per person per session for the coaches, accounted for from profits. | September 2025 – Ongoing | 5% increase in local shinty club membership within 3 years. At least 50 visitors per year sign up for follow-up shinty sessions | Tracking registrations for shinty clubs Follow-up surveys with participants Club participation statistics |
| Economic Impact through Tourism and Local Business Engagement – The exhibition will attract new visitors to Bught Park and Inverness, contributing to the local economy through increased footfall in hotels, restaurants, and local attractions. | Tourists & visitors to the area | Increased visitor spending in the local economy More visitors explore cultural attractions in Inverness | Marketing strategy, collaboration with Highlife Highland, VisitScotland, travel and tourism operators | Marketing Budget | July 2025 - Ongoing | Attracting 10,000 visitors annually by Year 3 25% of visitors engage with other local attractions, with a focus on Inverness Castle where the Camanchd Cup will be on display. | Partnership evaluation Visitor data collection |
| Community Engagement and Legacy – The exhibition will serve as a community hub where local shinty clubs, history groups, and Gaelic speakers can gather, strengthening local identity and social connections. | Local community groups Shinty clubs Gaelic speakers Volunteers. | Heritage is protected, conserved, and revitalised Stronger community bonds formed through shared heritage appreciation | Project Manager time Shinty Memories Scotland collaboration | Covered in activity budget which will engage with a range of different groups. | September 2025 - Ongoing | 10+ community groups actively engaged in the exhibition’s evolution At least 50 volunteers contribute annually | Community feedback sessions from activity Tracking volunteer hours Annual surveys with club leaders |
| Financial Sustainability through Revenue Generation – The tiered experience model will ensure the exhibition generates sustainable revenue through donations, ticketed experiences, and merchandise.. | All visitors Sports fans Schools Event organisers | Exhibition sustains itself financially Revenue reinvested in exhibition updates and programming | Ticketing system Merchandise sales infrastructure Event programming | Merchandise budget and activity plan budget reference above | July 2025 - Ongoing | Generating £50,000 in donations and ticketed experiences annually by Year 4 Merchandise sales accounting for 10% of total income | Financial performance tracking Sales data analysis |
| Encouraging Gaelic Language Use and Cultural Appreciation – Gaelic will be embedded in exhibition materials, guided experiences, and digital content, ensuring it is promoted as part of shinty’s cultural heritage. | Gaelic learners Fluent speakers Cultural enthusiasts General visitors | Gaelic language promoted and normalised in a sports heritage setting Visitors engage with Gaelic interpretation | Bilingual exhibition materials, Gaelic-speaking guides Gaelic media content | Translation costs and bilingual interpretation, both built in and agreed with Lateral North. | July 2025 - Ongoing | At least 20% of exhibition materials interacted with in Gaelic 500+ engagements with Gaelic digital content annually | Visitor surveys on Gaelic engagement Online analytics on Gaelic media Feedback from Gaelic partners, namely Bòrd na Gàidhlig |
| Engagement with Digital Audiences – The exhibition will extend beyond physical visitors through virtual reality elements (Tier 2), interactive online resources, and digital storytelling. | Digital heritage users Remote visitors Younger audiences | Heritage information is more accessible The exhibition reaches audiences over 100 miles from Inverness | VR technology digital content production Website integration | Covered under digital engagement budget, with Lateral North undertaking the building of the digital environment. | September 2025- Ongoing | 5,000 digital interactions per year 8 classroom-based VR experience delivered in Year 1 | Online engagement analytics VR usage data Social media metrics |